## Product backlog
Snake Game
ID | Description | Milestone # | 1 | 2 | 3
|  | Hours needed for Release as in the beginning of the milestone | 28 | 38 | 41
1 | Create classes required for the project |  | 8 | 0 | 0
2 | Create application skeleton of the game |  | 5 | 0 | 0
3 | Determine the data members and methods of each class |  | 15 | 0 | 0
Milestone 1 | User management and blueprint of classes
4 | Make constructors of classes |  | 0 | 8 | 0
5 | Make the definition of member functions of classes |  | 0 | 23 | 0
6 | Implement authentication of the users |  | 0 | 4 | 0
7 | Implement registeration of the users |  | 0 | 3 | 0
Milestone 2 | Minimal working version
8 | Create the visible gameboard using graphics |  | 0 | 0 | 11
9 | Complete Snake class and graphics |  | 0 | 0 | 18
10 | Attach classes to each other |  | 0 | 0 | 9
11 | Cleaning of GUI and commenting |  | 0 | 0 | 3
Release | Running version
| Hours in the whole backlog |  | 28 | 38 | 41